# Free sample from BA Toolkit Complete

This is one filled example from BA Toolkit Complete, which contains 59 Word and Excel files. The project, people and figures are fictional: a status report for Meridian Mutual's customer portal, Release 1.

The example shows a template completed through one reporting period, from the RAG status and achievements to the risks, decisions and next steps.

IDs such as FSF-11 or GOV-01 refer to other files in the toolkit, which are not part of this sample. The full toolkit is available at baaicollective.com.

# Project Status Report

BA Toolkit v9.3 | October 2026

Fictional example. Meridian Mutual customer portal, Release 1. Position as at 12 June 2026, the close of UAT cycle 1. All names, figures and decisions are fictional.

| Project Name | Meridian customer portal, Release 1 |
| --- | --- |
| Reporting Period | Week ending Friday 12 June 2026 (UAT cycle 1 close) |
| PM | Kevin Marlow, Project Manager |
| BA Lead | Laura Simmons, Lead BA |
| RAG Status | Amber |

# 1. Executive Summary

Overall status is Amber. UAT cycle 1 finished on its revised dates: of 35 designed tests, 26 were executed (21 Pass, 5 Fail), 2 were Blocked and 7 were Not run; the 16 Approved requirements in BL-02 are largely sound, with five outstanding defects and no Critical defect. The next focus is the three decisions that unlock REQ-001, REQ-002 and REQ-005 (DEC-09, DEC-01, DEC-08) between 17 and 19 June, because go-live on 14 July has no float left.

# 2. Overall Status

| Dimension | Status | Notes |
| --- | --- | --- |
| Schedule | Amber | UAT cycle 1 ran 8 to 12 June after CR-001 moved it by five working days. Go-live on 14 July holds but float is used. If DEC-09 or DEC-01 slip past 19 June, go-live moves one week for each week of delay (RISK-03). |
| Budget | Green | Spend to date £268,400 against £281,000 planned. Forecast at completion £401,000 against £420,000 approved. CR-001 (£11,700) came from contingency, leaving £23,300. |
| Scope | Amber | 20 requirements: 16 Approved (BL-02), 3 Under Review (REQ-001, 002, 005), 1 Draft (REQ-004). REQ-004 is a Release 2 candidate unless OQ-006 is answered by 26 June. |
| Resources | Green | UAT delegates Sam Whitaker and Zoe Barrett were available for cycle 1; release for cycle 2 is not yet confirmed (RISK-05). The Security Owner's time is committed on 17 to 19 June (ISS-03). |
| Quality | Amber | 5 outstanding defects: 3 High (DEF-001, 002, 004), 2 Medium (DEF-003, 007); 2 closed (DEF-005, 006). UAT sign-off is Deferred: criteria not met, with 3 in-scope tests not executed, 3 High defects outstanding and a pass rate of 81% against 95% required (GOV-04, gate G3). |

RAG basis (template section 2.1): Schedule Amber, float is used up and a recovery plan exists; Budget Green, forecast at completion is 4.5% under the approved £420,000; Scope Amber, DEC-08 is overdue and holds REQ-005; Resources Green, named people are confirmed for the next 2 weeks; Quality Amber, High defects are outstanding with fix dates inside the plan. Overall Amber is the worst dimension.

# 3. Key Achievements This Period

Completed UAT cycle 1: 35 tests designed, 26 executed, 2 Blocked, 7 Not run; 7 defects raised and linked to their tests.

Assessed and approved CR-001 in five working days and issued baseline BL-02 on 22 May with five requirements at v2.

Closed six of the twelve open questions in FSF-13 (OQ-004, OQ-007, OQ-008, OQ-009, OQ-010, OQ-012), each answered by a named decision (DEC-06, DEC-03, DEC-04, DEC-02, DEC-07, DEC-10).

Closed two defects found in cycle 1 within three days, including a reset-request timing leak (DEF-006).

# 4. Issues & Blockers

| ID | Description | Owner | Target Date | Status |
| --- | --- | --- | --- | --- |
| ISS-01 | UAT data has no Suspended-account scenarios, so T-021 is Blocked. Fresh synthetic extract requested. Waived for cycle 1 under DEC-13 (8 June); closes before cycle 2. | Ruth Ellison, Test Lead | 17 June 2026 | In Progress |
| ISS-02 | The performance test environment is not available until 15 June, so T-024 (REQ-101) could not run in cycle 1. Environment booked for 15 to 19 June. Waived for cycle 1 under DEC-13 (8 June); T-024 runs before cycle 2. | Callum Reid, Technical Lead | 15 June 2026 | In Progress |
| ISS-03 | Security Owner is committed on 17, 18 and 19 June (fraud review, Steering Group, DEC-01), leaving no slack. | Kevin Marlow, Project Manager | 15 June 2026 | Open |
| DEP-01 | CRM stub with controllable failures for the retry and alert tests (T-031 Blocked; T-005 design). Resource clash with a CRM release on 15 June. | Marcus Bell, CRM Owner | 16 June 2026 | At Risk |

Open questions (from FSF-13 Summary): total 12 | percent closed 50% | overdue 1 (OQ-005, which blocks REQ-005; recorded against RISK-06 and RISK-03).

# 5. Risks

Top five of nine active risks, ranked by residual score on the GOV-01 Dashboard. Three risks are Red before response (RISK-03, RISK-04, RISK-09); none is Red after response.

| ID | Risk | Residual | Trend | Response and owner |
| --- | --- | --- | --- | --- |
| RISK-03 | DEC-01 and DEC-09 slip beyond 19 June, so REQ-001 and REQ-002 cannot be built and tested before go-live on 14 July. | Amber (12) | Stable | Decision papers issued; fraud review 17 June; Steering Group 18 June. If a decision slips, go-live moves one week per week of delay, or REQ-001 and REQ-002 move to a second release. Escalate on 19 June. Kevin Marlow, Project Manager. |
| RISK-09 | Go-live on 14 July has no float, which puts pressure on the exit and readiness gates. | Amber (10) | New | No go-live until GOV-04 gates G3 and G4 are passed or the Executive Sponsor approves conditions. Amir Patel, Product Owner. |
| RISK-04 | The identity-verification service is not chosen until DEC-09, so it may not be connected for the cycle 2 tests (T-001, T-009). | Amber (9) | New | Shortlist two services before 18 June; sandbox access by 1 July. Callum Reid, Technical Lead. |
| RISK-06 | A failed CRM synchronisation may go unalerted in live running: DEC-08 is undecided and T-005 and T-031 have not run. | Amber (9) | Stable | Decide DEC-08 by 19 June; CRM stub by 16 June; interim morning check of the exception queue. Callum Reid, Technical Lead. |
| RISK-01 | Compliance sign-off may be delayed because Compliance SME time is limited. | Amber (8) | Stable | Weekly compliance review held since 17 March; decisions logged against the delegation. Laura Simmons, Lead BA. |

# 6. Upcoming Milestones

| Milestone | Target Date | Owner |
| --- | --- | --- |
| Fraud-team review of SMS exposure | 17 June 2026 | Neil Fraser, Security Owner |
| Steering Group decision DEC-09 | 18 June 2026 | Sarah Chen, Executive Sponsor |
| DEC-01 and DEC-08 decisions | 19 June 2026 | Neil Fraser, Security Owner; Callum Reid, Technical Lead |
| UAT cycle 2 | 6 July 2026 | Ruth Ellison, Test Lead |
| Go or no-go (gate G4) | 13 July 2026 | Amir Patel, Product Owner |

# 7. Decisions Needed

DEC-09: identity-verification method and assurance level for registration. Owner: Sarah Chen, Executive Sponsor, by 18 June 2026. If late: REQ-001 stays Under Review; registration cannot go live without an agreed control.

DEC-01: MFA channel, segments and recovery. Owner: Neil Fraser, Security Owner, by 19 June 2026. If late: REQ-002 stays Under Review; Sprint 4 build and cycle 2 tests cannot be planned.

DEC-08: alert after a CRM failure that recovers. Owner: Callum Reid, Technical Lead, by 19 June 2026. If late: REQ-005 stays Under Review; T-005 cannot be designed to an agreed result.

Decided this period: DEC-13 (8 June 2026), Amir Patel, Product Owner, under SRC-07 v1. The two G2 entry criteria ISS-01 and ISS-02 were waived for UAT cycle 1 only; both close before cycle 2 and neither is waived for gate G3. The Decision Log now holds 13 decisions: 10 Approved and 3 Pending (DEC-01, DEC-08, DEC-09).

# 8. Actions

| ID | Action | Owner | Due Date | Status |
| --- | --- | --- | --- | --- |
| A001 | Table DEC-09 at Steering Group with the Compliance recommendation | Laura Simmons, Lead BA | 18 June 2026 | Open |
| A002 | Confirm the date and attendees for the fraud-team review | Kevin Marlow, Project Manager | 15 June 2026 | Open |
| A003 | Supply a synthetic data extract with Suspended and Archived accounts (ISS-01) | Ruth Ellison, Test Lead | 17 June 2026 | Open |
| A004 | Confirm the CRM stub delivery date (DEP-01) | Marcus Bell, CRM Owner | 16 June 2026 | Open |
| A005 | Fix DEF-001, 003, 004 and 007 by 3 July; retest all outstanding defects in cycle 2 (6–10 July) | Callum Reid, Technical Lead | 3 July 2026 | Open |
| A006 | Issue the cycle 1 test report to the Product Owner | Ruth Ellison, Test Lead | 12 June 2026 | Done |

# 9. How to populate this report from the registers

Copy each figure from the register that owns it, on the reporting date, so the report and the registers always agree. Do not retype a number that a register can give you. The last column shows the value used in this example.

| Report item | Take it from | Value in this example |
| --- | --- | --- |
| Schedule RAG and milestones | Project plan; GOV-04 Stage Gates sheet, rows G1 to G4: column E (Planned Date) and columns F to J (mandatory criteria counts) | Gate G3 UAT exit is Fail (Deferred); G4 not yet due; go-live 14 July, no float |
| Budget RAG: spend, forecast, contingency | Finance Business Partner's cost report; CR costs from FSF-12 section 7 (Cost row) | £268,400 against £281,000; forecast £401,000 against £420,000; contingency £23,300 |
| Scope: requirements by status | FSF-05 Dashboard: B2 (total), B5 to B9 (Status), B14 to B19 (Delivery status); FSF-11 Summary: Decision not approved | 20: 16 Approved, 3 Under Review, 1 Draft |
| Tests: designed, executed, Pass, Fail, Blocked, Not run | FSF-17 Dashboard: B2 to B6 (designed, Not run, Pass, Fail, Blocked); B10 and B11 (executed, pass rate) | 35 designed; 26 executed (21 Pass, 5 Fail); 2 Blocked; 7 Not run |
| Quality: outstanding defects, exit criteria | FSF-17 Dashboard B8 (outstanding defects); UAT Sign-off B26 to B31 (exit-criteria check); GOV-04 Stage Gates, row G3 | 5 outstanding (3 High, 2 Medium); 3 tests not executed; pass rate 81% against 95% |
| Open-questions line | FSF-13 Summary: B3 (total), B8 (percent closed), B9 (overdue) | 12 total; 50% closed; 1 overdue (OQ-005) |
| Risks table | GOV-01 Dashboard: A6 to H11 (top five residual risks, with trend); D16 (residual Red) and D19 (inherent Red) | RISK-03 (12), RISK-09 (10), RISK-04 (9), RISK-06 (9), RISK-01 (8) |
| Issues and dependencies | GOV-01 Issues sheet (open, with target date) and Dashboard D29 to D31; Dependencies sheet (At Risk or Late) and Dashboard D40 | ISS-01 to ISS-03; DEP-01 At Risk |
| Decisions needed | GOV-02 Summary B5 (Pending) and the Decision Log filtered to Pending; FSF-05 Dashboard B6 (Under Review) | DEC-09, DEC-01, DEC-08 |
| Actions | Project action list: open actions from this report and the last | A001 to A006 |