## Read me
Traceability matrix: a filled example
Free sample from BA AI Collective. The worked case from the guide at baaicollective.com/resources/requirements-traceability-matrix-example
1 | Northgate Bank wants a warning screen before a business customer pays a new payee, and a hold of up to 30 minutes on payments above £10,000 to a new payee.
2 | Matrix: six requirements, each traced to its source, the decision that approved it, its owner, design section and tests. The Check column flags the gaps.
3 | Sources and Decisions: where each requirement came from and who decided it, so "who asked for this?" always has an answer.
4 | Tests: each test points back to a requirement. The Check column flags any test that traces to nothing (TC-09 does, on purpose).
5 | Checks: the three questions the matrix answers in seconds: untested requirements, orphan tests, and requirements nobody has approved.
6 | Change log: the Head of Fraud moves the hold from 30 to 60 minutes. The matrix shows the impact straight away: FS-4.1 and tests TC-04 to TC-06.
7 | Try it: change a Test IDs cell to "None yet", or add a test with a requirement ID that does not exist, and watch the checks update.
Northgate Bank and everyone in it are fictional. The Starter toolkit includes the Traceability Matrix template behind this example: baaicollective.com/toolkits
Free to use and adapt for your own work. Please don't resell it. BA AI Collective is a trading name of Quantum Sphere Consulting Limited.

## Matrix
Requirements traceability matrix
One behaviour per row. Owner = the person with authority to confirm, left blank until someone does. Status kept honest.
Req ID | Requirement | Source | Decision | Owner | Design ref | Test IDs | Status | Check
REQ-01 | Show a warning screen before the first payment to a new payee | SRC-01 | DEC-01 | Product owner | FS-3.1 | TC-01, TC-02 | Approved
REQ-02 | Customer can confirm and continue from the warning screen | SRC-01 | DEC-01 | Product owner | FS-3.2 | TC-03 | Approved
REQ-03 | Hold payments above £10,000 to a new payee for up to 60 minutes (was 30: see change log CH-01) | SRC-02; SRC-05 | DEC-02; DEC-04 | Head of Fraud | FS-4.1 | TC-04, TC-05, TC-06 | Approved
REQ-04 | Notify the customer by text message when a payment is held | SRC-02 | None yet | Head of Fraud | FS-4.3 | TC-07 | Open: wording not agreed
REQ-05 | Record every warning shown, with the customer's response | SRC-03 | DEC-03 | Compliance | FS-5.1 | None yet | Approved
REQ-06 | Let a branch manager release a held payment | SRC-04 | None yet |  | Not designed | None yet | Proposed

## Sources
Sources
Where each requirement came from. A source that says "meeting" tells nobody anything; one with a date and a role can be checked.
Source ID | What it is | From (role) | Date | Seen by steering group?
SRC-01 | Fraud review minutes, action 4 | Fraud review panel | 2026-10-01 | Yes
SRC-02 | Email from Head of Fraud: hold and text notification | Head of Fraud | 2026-10-06 | No
SRC-03 | Audit workshop notes | Compliance | 2026-10-08 | No
SRC-04 | Operations call: branch release of held payments | Operations lead | 2026-10-09 | No
SRC-05 | Email from Head of Fraud: hold extended to 60 minutes | Head of Fraud | 2026-10-15 | No
Notice: the hold (REQ-03) rests on emails the steering group never saw. The matrix makes that visible before someone asks.

## Decisions
Decisions
Who decided what, and where it is recorded. A requirement is approved by a decision, not by being written down.
Decision ID | Decision | Made by | Date | Recorded in
DEC-01 | Warn customers before the first payment to a new payee; the customer may confirm and continue | Product owner | 2026-10-02 | SRC-01 action 4
DEC-02 | Hold first payments above £10,000 to a new payee for up to 30 minutes | Head of Fraud | 2026-10-06 | SRC-02
DEC-03 | Record every warning shown and the customer response, for audit | Compliance | 2026-10-08 | SRC-03
DEC-04 | Hold extended from 30 to 60 minutes (supersedes the period in DEC-02) | Head of Fraud | 2026-10-15 | SRC-05; change CH-01
REQ-04 and REQ-06 have no decision yet: one is still being argued over, the other was only raised on a call.

## Tests
Test cases
Backward traceability: every test should point at a requirement in the Matrix.
Test ID | Traces to Req ID | What it checks | Check
TC-01 | REQ-01 | Warning shown on first payment to a new payee
TC-02 | REQ-01 | No warning on a second payment to the same payee
TC-03 | REQ-02 | Customer confirms and the payment continues
TC-04 | REQ-03 | Payment of £10,000.01 to a new payee is held
TC-05 | REQ-03 | Payment of exactly £10,000 is not held
TC-06 | REQ-03 | Held payment releases after the hold period
TC-07 | REQ-04 | Text message sent when a payment is held
TC-09 |  | Warning screen displays correctly on a tablet

## Checks
The three checks
Recalculates as you edit the Matrix and Tests sheets.
Check | Count | What to do
Approved requirements with no test (forward gap) |  | Raise at the test readiness review. Here: REQ-05.
Tests that trace to no requirement (backward gap) |  | Either a requirement is missing or the test is out of scope. Here: TC-09, tablets.
Requirements not yet approved (scope watch) |  | Keep design effort off them until the owner confirms. Here: REQ-06.
Requirements with no owner |  | Find who has authority to confirm. Do not guess.
Approved requirements with no recorded decision |  | Find who decided, and when. Here: none, every approved row has one.

## Change log
Change log
When a requirement moves, record the new source and the impact. The matrix tells you the impact.
Change ID | Date | Req ID | Change | New source | Impact found through the matrix
CH-01 | 2026-10-15 | REQ-03 | Hold extended from 30 to 60 minutes | SRC-05 | Design FS-4.1; tests TC-04, TC-05, TC-06. Raised as one change request with three tests and one design section.